## Tast Plan
Click here to show the Test Plan

## Test Secnario
Project Name | startech
Reference Document | FRS
Created By | Tamanna Akter
Creation Date
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | No. of Test Cases
TS_001 |  | Validate the URL in different browsers | P0 | 1
TS_002 |  | Validate the "Register Account / Sign up" functionality | P0 | 8
TS_003 |  | Validate the "OTP" functionality | P1 | 16
TS_004 |  | Validate the "Log In" functionality | P0 | 31
TS_005 |  | Validate the "Forgot Password" functionality | P2 | 50

## Teat Case
Product Name |  | startech | Test Case Start Date | 25/09/2023 | Test Execution Start Date
Module Name |  | Account | Test Case End Date | 27/09/2023 | Test Execution End Date |  |  |  |  | TEST CASE
Epic |  |  | Test Case Developed By | Tamanna Akter | Browser (tested) | Yes |  |  |  | PASS | 55
Developer Name (Test Lead) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  | Fail | 7
Test Executed By | [9 empty] | Not Executed | 0
[10 empty] | Out of Scope | 0
[10 empty] | Total | 62
SL NO. | Module | Type of Testing | Features | Test Cases Description | Expected Result | Actual Result | Test Data | Reproducing Steps | Bug Screenshot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'Star Tech' 3. Goto the website |  |  | Passed
2 | User Management | User Interface Testing | Register | Checking all spelling & grammatical mistakes on the register page. | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on" Register" button at the right corner |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Hover over every fields |  |  | Passed
4 |  |  |  | Verifying the font, text color, style and alignment of the fields | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Check the font, text color, style and alignment |  |  | Passed
5 |  |  |  | Verifying password should be protected and encrypted | Password should be encrypted | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Check the password encrypted |  |  | Paassed
6 |  |  |  | Verifying mandatory field is marked with a red asterisk(**) | Red asterisk should be present | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Check the red asterisk |  |  | Passed
7 |  |  |  | Verifyingan eye icon added to the password and confirm the password field. | Eye icon should be visible on the field | Not found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. given the valid name, gmail, phone no & type the OTP 4. Click the password field | Password view functionality |  | Failed
8 |  | Functional Testing |  | verifying users can register successfully by entering valid credentials. | Should allow user to successfully register | Found as per expectation | First Name: Tamanna Last Name: Akter Email: tamannaakter180912@gmail.com Telephone: 01998322964 Password:88471543 | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Enter all valid credentials in the register field |  |  | Passed
9 |  |  |  | Checking alert message for all mandatory fields are blank and clicks on the register button | Should pop an error message | Found as per expectation | blank firld | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Keeping blank in each field and checking |  |  | Passed
10 |  |  |  | Checking the error message when first name field blank | Should not accept the provided input | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Keeping blank in first name field and checking |  |  | Passed
11 |  |  |  | Checking the error message when last name field blank | Should not accept the provided input | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Keeping blank in last name field and checking |  |  | Passed
12 |  |  |  | Inputing first name and last name with special characters, numbers, decimal numbers | Should not accept the provided input | Not found as per expectation | First Name: er#$%66 Last Name: 88765 | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Enter numbers, decimal,special character in firstand last name field | Numeric & special character |  | Failed
13 |  |  |  | Checking the verify mail in the email address | Should verify the account | Found as per expectation | Valid email :tamannaakter180912@gmail.com | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Fill the email address with already registered email 4. Fill the all valid information in the mandatory field 5. Go to mail address to check the verify mail |  |  | Passed
14 |  |  |  | Checking by invalid email formate | User is not allowed to register an account | Found as per expectation | Invalid email: asdr@#$567.com | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3.Enter the invalid email formate |  |  | Passed
15 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Typing the same email in the email field' |  |  | Passed
16 |  |  |  | Validating phone number can only be used one time | Should not allow user to register and display a pop message | Found as per the expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Typing the same phone number |  |  | Passed
17 |  |  |  | Verifying blank the phone number field and fill the other field with valid credentials with click the register field | Should display an error message | Found as per the expectation | First Name:Tamanna Last Name: Akter Email:tamannaakter180912@gmail.com Phone No.:blank | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. keeping the blank phone number field |  |  | Passed
18 |  |  |  | Verifying the phone no.field with special character | Should display an error message | Found as per expectation | phone number:@#$%% | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3.Entering the special character in phone number field |  |  | Passed
19 |  |  |  | Entering the phone number with alphanumeric characters | Should display an error message | Found as per expectation | phone number:0123thgy | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Typing the alphanumeric phone number |  |  | Passed
20 |  |  |  | Checking the phone number can be copied and paste in the field or not | Should not be coppied | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3.Paste the copied phone number |  |  | Passed
21 |  |  |  | Verifying the OTP input field doesn't allow alphabet | Should display an error message | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3.Typing all valid information in mandatory field 4. Typing OTP |  |  | Passed
22 |  |  |  | Entering the wrong OTP in the field | Should display an error message | Found as per expectation | N/A | 1.Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3.Typing all valid information in mandatory field 4. Typing wrong OTP |  |  | Passed
23 |  |  |  | Verify whether the "Resend OTP" button is given | Should be visible a "Resend OTP" | Not Found as per the expectation | N/A | 1.Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3.Typing all valid information in mandatory field 4. Typing OTP 5.Checking the Resend OTP option | Resend OTP functionality |  | Failed
24 |  |  |  | Entering the wrong password in the "Confirm New Password" field | Should display an error message | Found as per expectation | N/A | 1.Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3 Typing wrong password |  |  | Passed
25 |  |  |  | Verifying the confirm new password field keeping blank and click the register button | Should display an error message | Found as per expectation | N/A | 1.Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3 Keeping confirm new password field |  |  | Passed
26 |  |  |  | checking whether the name field & password field displays the minimum character length with a message | Should display a message | Not found as per expectation | N/A | 1.Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3 Typing all password & name in the field & check the character length message | Maximum & minimum length |  | Failed
27 |  |  |  | Verify captcha is added to the form or not due to security | Should be present captcha | Not found as per the expectation | N/A | 1.Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3 Typing all valid information 4. Checking the captcha field | Captcha functionality |  | Failed
28 |  |  |  | verifying blank spaces and clicks on the register button an error message should be shown. | The error message should be pop up on the display | Found as per expectation | N/A | 1.Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3 keeping blank space in all the field |  |  | Passed
29 |  | Usability Testing |  | Checking copy & paste in every field | Should copy and paste text from fields without password field | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
30 |  |  |  | keyboard "tab" button functionality | Should switch to another field | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2. Click on Register button at the right corner 3. Enter tab key on the every field |  |  | Passed
31 |  | User Interface Testing | Log In | verifying the login screen will appear after clicking on a login link or login button | Should run in different browsers | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Check the spelling and grammar |  |  | Passed
32 |  |  |  | Verifying all login-related elements and fields are present on the login page | Should be present all necessary fields | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" |  |  | Passed
33 |  |  |  | Verifying the alignment of displayed | Should be present all necessary fields | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" |  |  | Passed
34 |  |  |  | Verifying that the size, color, and UI of different elements | Should as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" |  |  | Passed
35 |  |  |  | Verifying the login page of the application and aligns properly on different screen resolutions and devices. | The cursor should blinked while click on the text field | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" |  |  | Passed
36 |  |  |  | Verifying login page title.& "Login" button hovering or not | Should be perfect as per as requirement | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. hover over the "Login" button |  |  | Passed
37 |  | Functional Testing |  | Verifying that the user will be able to Login with their account with the Vvalid credential | User should able to Login | Found as per expectation | Email: tamannaakter180912@gmail.com Telephone: 01998322964 Password:88471543 | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.Enter password & email |  |  | Passed
38 |  |  |  | Verifying that the user can access all controls and elements by pressing the Tab key from the keyboard | Should be useable the "Tab" key | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" |  |  | Passed
39 |  |  |  | Verifying that the user can log in by entering valid credentials and pressing Enter key. | Should be allow to user | Found as per expectation | Email: tamannaakter180912@gmail.com Telephone: 01998322964 Password:88471543 | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.Enter password & email 4.enter "Enter" key on the keyboard |  |  | Passed
40 |  |  |  | Verifying enterian email address and leaving the password field blank. | Should display an error message | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.Enter blank password |  |  | Passed
41 |  |  |  | Verifying enterian password and leaving email address field blank. | Should display an error message | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.Enter blank email address field |  |  | Passed
42 |  |  |  | Keeping email & password fields blank | Should be blanked to put data and showing an error message on the display | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.Enter blank password & email address field |  |  | Passed
43 |  |  |  | Checking login wrong credentials in email and password field | Should display an error message | Found as per expectation | Email:tamanna@#$.com@#$ password:8907 | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter inalied credentials in the email & password field |  |  | Passed
44 |  |  |  | Checking login first space credentials in email and valid password field | Checking login first space credentials in email and valid password field | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter first space credentials email in the field and valid pass word |  |  | Passed
45 |  |  |  | Verifying that the password entered should be in encrypted form. | Should be encrypted the entered password | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter valid email in the field and valid pass word |  |  | Passed
46 |  |  |  | Verifying whether an eye icon is added to the password field or not & mandatory field is marked with a red asterisk (***) | Should as per requirement | Not found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter valid email in the field and valid pass word | Not added asterisk & eye icon |  | Failed
47 |  |  |  | Verifying logged-in user copies the URL and pastes it into a new browser window, it should redirect to the login page | Should URL copy and paste text | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter valid email in the field and valid pass word 4. CopyURl and past it new browser |  |  | Passed
48 |  |  |  | Verifying user signs in, on the home page, there is no need for displaying Sign Up or Try Now, etc (if the user logged in) | Should not show sign Up or Try now when signs in the home page | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter valid email in the field and valid pass word 4. Logged in home page & don’t show sign up button |  |  | Passed
49 |  |  |  | Checking while typing in the password field there will be display a "Forgot Password" link under the password field | hould display a "Forgot Password" link | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter the password in the field & check the "Forgot Password" link |  |  | Passed
50 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter the password in the field & check the "Forgot Password" link |  |  | Passed
51 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Account should be temporarily restricted and a message should be display | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Multiple click the "Forgot Password" link |  |  | Passed
52 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" In" button at the right corne 3.Click on 'Forgot Password' 4. Check the email |  |  | Passed
53 |  |  |  | Verifying the valid phone number | Should be sent message | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" In" button at the right corne 3.Enter phone number |  |  | Passed
54 |  |  |  | Verifying the invalid credentials phone number | User get an error message on the display | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.Enter invalid phone number |  |  | Passed
55 |  |  |  | Verifying "Remember Me" checkbox on the login page. | Checkbox should be present | Not found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" | Remember me missing |  | Failed
56 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent message in valid email address | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.Go to check the mail |  |  | Passed
57 |  |  |  | Checking the email message grammar & spelling should be correct. | Sending message should be grammatically correct | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.Go to check the mail message grammatically |  |  | Passed
58 |  |  |  | Checking the phone number message grammar & spelling should be correct. | Sending message should be grammatically correct | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3.click the forget passwor & check the phone number message grammatically |  |  | Passed
59 |  |  |  | Verifying the displayed error message grammar should be correct. | The error message should be grammatically correct | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Check the grammartical error message |  |  | Passed
60 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Copy paste text in every field |  |  | Passed
61 |  |  |  | Checking keyboard tab button functionality | Should switch to another field & hilighting text | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In"3. Enter tab in every field |  |  | Passed
62 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Found as per expectation | N/A | 1. Goto the URL https://www.startech.com.bd 2.Click on "Log In" button at the right corner& check the "Log In" 3. Enter "Enter" in every field |  |  | Passed

## Teat Summary Report
Test Case Report | [5 empty] | Result
Project Name | Star Tech ¦ Online Shopping platform |  |  |  |  | Status | Total
Module Name | Account |  |  |  |  | Pass | 55
Feature Name | Register & Log In |  |  |  |  | Fail | 7 | New Features: | Testing Scope | Testing Environment: Google Chrome Browser
Test Case Version | 1 |  |  |  |  | Not Executed | 0
Written By | Tamanna Noshi |  |  |  |  | Out of Scope | 0
Excuted By | Tamanna Noshi
Reviewed By
TEST EXECUTION REPORT
Test Case | Pass | Fail | Not Excuted | Out of Scope | Total Test Case
| 55 | 7 | 0 | 0 | 62
LIMITATIONS
Documents |  | Received |  | Useful
PRD |  | No |  | No
User Story |  | No |  | No
| Testing Type in Scope |  | Description
YES/NO. juctification(If No:) | Functional Testing |  | Functional Testing is a type of software testing that validates the software system against the functional requirements/specifications.
YES/NO. juctification(If No:) | Integration Testing |  | Integration testing is a type of software testing in which the different units, modules or components of a software application are tested as a combined entity.
YES/NO. juctification(If No:) | Negative Testing |  | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
YES/NO. juctification(If No:) | Usability Testing |  | This is done from an end user’s perspective to determine if the system is easily usable.
YES/NO. juctification(If No:) | Browser Compatibility Testing |  | Browser compatibility test is an assessment used to ensure a software application is properly working across different browsers, databases, operating systems (OS), mobile devices, networks and hardware.
YES/NO. juctification(If No:) | Boundary Value Tesing |  | Boundary testing is the process of testing between extreme ends or boundaries between partitions of the input values. So these extreme ends like Start- End, Lower- Upper, Maximum-Minimum, Just Inside-Just Outside values are called boundary values and the testing is called “boundary testing”.
YES/NO. juctification(If No:) | Risk Based Testing or Regression Testing |  | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
Serial_01
Issue : Eye icon not added to the password and confirm the password field.
Reproducing Steps:
1. Goto the URL : https://www.startech.com.bd 2. Click on "Register" button at the right corner 3. given the valid name, gmail, phone no & type the OTP 4. Click the password field
Environment: Production
Module: Register
Priority: P2 (medium)
Severity: 3 (major)
Screenshot: Eye icon not added to the password and confirm the password field
Expected: Eye icon in password & confirm the password field
Responsible QA: Tamanna Noshi
Bug Reporting
Serial_02
Issue : Captcha is not added to the register form due to security.
Reproducing Steps:
1. Goto the URL : https://www.startech.com.bd 2. Click on "Register" button at the right corner 3. given the valid name, gmail, phone no & type the OTP 4. Click the password field 5.Check captcha.
Environment: Production
Module: Register
Priority: P4 (Low)
Severity: 4 (minor)
Screenshot: Captcha is not added to the register form
Expected: Captcha is added in the register form
Responsible QA: Tamanna Noshi
Bug Reporting
Serial_03
Issue : Resend OTP button is missing
Reproducing Steps:
1. Goto the URL : https://www.startech.com.bd 2. Click on "Register" button at the right corner 3. given the valid name, gmail, phone no & type the OTP 4. Search resend OTP
Environment: Production
Module: Register
Priority: P2 (medium)
Severity: 3 (major)
Screenshot: Resend OTP link is missing on the display
Expected: Resend OTP button is added on the register form
Responsible QA: Tamanna Noshi
Bug Reporting
Serial_04
Issue : Accept numeric values and special characters in the name field
Reproducing Steps:
1. Goto the URL : https://www.startech.com.bd 2. Click on the "Register" button in the right corner. 3.ckick on the "Register" link and go to the sign up page. 4. Type a combination of number and special character
Environment: Production
Module: Register
Priority: P4 (Low)
Severity: 4 (minon)
Screen record: Accept numeric value & special character
Expected: Should not be pasted the numeric values and special characters in the name field
Responsible QA: Tamanna Noshi
Bug Reporting
Serial_05
Issue: Boundary value not displayed while typing in the name field & password field
Reproducing Steps: Boundary value not displayed while typing in the name field & password field
1. Goto the URL : https://www.startech.com.bd 2. Click on the "Register" button in the right corner. 3.ckick on the "Register" link and go to the sign up page. 4. type some alphabets special character
Environment: Production
Module: Register
Priority: P2 (medium)
Severity: 3(major)
Screenshot: Maximum & minimum length on the name field and password field
Expected: Should display boundary value while typing in the name field & password field
Responsible QA: Tamanna Noshi
Bug Reporting
Serial_06
Issue: Mandatory field is not marked with a red asterisk (***) & password view functionality missing
Reproducing Steps:
1. Goto the URL : https://www.startech.com.bd 2. Click on the "Register" button in the right corner. 3.ckick on the "Log in" link
Environment: Production
Module: Log In
Priority: P2 (Medium)
Severity: 3 (major)
Screenshot: Missing red asterisk & eye icon
Expected: Should mandatory field marked asterisk sign and eye icon added password field
Responsible QA: Tamanna Noshi
Bug Reporting
Serial_07
Issue: Remember Me checkbox not added on the login page
Reproducing Steps:
1. Goto the URL : https://www.startech.com.bd 2. Click on the "Register" button in the right corner. 3.ckick on the "Log in" link
Environment: Production
Module: Log In
Priority: P4 (Low)
Severity: 4(minor)
Screenshot: Not added remember me checkbox
Expected: Should remember me checkbox visible on the display
Responsible QA: Tamanna Noshi

## Test Metrics
Test Metrics
Serial | Metrics | Description | Result
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (62/62)*100=100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/62)*100=0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (55/62)*100= 88.71 %
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (7/62)*100=11.29 %
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/62)*100=0
6 | Defect Density | No.of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Recommendation
GENERAL INFORMATION
Test stage | Unit performance | Functionality Regression | Integration Acceptance | System Pilot |  | Interface
Specify the testing stage for this test case
Date | mm/dd/yy |  | System Date,If Applicable |  | mm/dd/yy
Tester: | Specify the name (s)of who is testing this case scenario. |  | Test Case Number |  | Specify the unique test number assigned to the test case
Test case Description: | Provide a brief description of what functionality the test case
Results: | Pass Fail |  | Incident Number,If Applicable: |  | Specify the unique identifier assingned to the incident.
INTRODUCTION
Requirement(s) to be tested: | Identify the requirments to be tested and include the requirment number and description from the Requirments Traceability Matrix
Roles and Responsibilites: | Describe each project team member and stakeholder involved in the test, and identify their associated responsibility for ensuring the test is executed appropriately
Set Up procedures: | Describe the sequence of actions necessary to prepare for execution of the test
Stop Procedures: | Describe the sequence of actions necessary to terminate the test
ENVIRONMENTAL NEEDS
Hardware: | Identify the qualities and configurations of the hardware required to execute the test case
Software: | Identify system and application software required to execute the test case.Specify any software that the test case will interact with.
Procedural Requirments: | Describe any constraints on the test procedures necessary to execute the test case
TEST
Test Items and Features: | Identify and describe the items and features that will be exercised by the test case.Group the test cases into logically related scenarios that test related items and features.For each item or feature,a reference to its associated requirment source should be include.
Input Specifications: | Define each input required to execute the test case and reference any required relationship between inputs.
Procedural Steps: | Describe the sequence of actions necessary to prepare and execute the test case.Provide detailed testprocedures for each test case; explain precisely how each test case will be executed.
Expected Results of Case: | Describe the outcome anticipated from the test case.Specify the criteria to be used to determine whether the item has passed or failed.
ACTUAL RESULTS
Output Specifications: | Define all of the outputs and features required of the test case and provided expected values. While executing the test, record and describe the visually observable outputs as they occure.Produce tangible evedence of the output such as ascreen print. At the conclusion,discreancies between the expected results and the actual results.